## Taxonomy
Cluster | Editorial Role | Item Status | Verification Grade | Rights Status | Selflo Fit | Source Type | Quote Type | Story Type | Tradition / Region | Release Readiness | Lĩnh vực cuộc sống (Life Area) | Chủ đề (Theme) | Cảm xúc / trạng thái (Emotion / State) | Hình thức nội dung (Content Form) | Mức Coverage
Exhaustion / Recovery / Work carryover | Recognize | Planned | A - Primary source | Public domain / likely | High | Primary text | Verbatim | Parable | Taoism | Not reviewed | Nội tâm & hiểu mình | Acceptance | Mệt mỏi | Quan sát trực tiếp | Missing
Self-compassion / Self-blame | Name | Collected | B - Authoritative secondary | Copyrighted / research only | Medium | Book | Working translation | Folktale | Stoicism | Research only | Cảm xúc | Agency | Cạn năng lượng | Ẩn dụ | Thin
Uncertainty / Choice / Agency | Permit | Needs Verification | C - Plausible / needs primary | Permission needed | Low | Speech | Published translation | Historical episode | Early Buddhism | Blocked - source | Công việc & mục đích | Attention | Lo lắng | Câu hỏi | Covered
Comparison / External standards / Values | Reframe | Verified | D - Disputed / internet-only | Selflo owned | Not reviewed | Letter | Paraphrase | Biography episode | Greek philosophy | Blocked - rights | Quan hệ | Boundaries | Sợ hãi | Nghịch lý | Rich
Attention / Noise / Deep focus | Distinguish | Needs Edit | N/A - Selflo Original | Unknown / verify |  | Poem | Proverb / traditional | Research case | Indian philosophy | Blocked - story dependency | Gia đình | Change | Bối rối | Tục ngữ / ca dao / thành ngữ
Learning / Failure / Quiet growth | Return agency | Shortlisted |  |  |  | Proverb | Selflo Original - AI-assisted draft | Journalism case | Vietnamese wisdom | Needs owner review | Lựa chọn & định hướng | Choice | Không chắc chắn | Thơ / văn vần
Change / Impermanence / Recovery |  | Release |  |  |  | Folk tradition | Selflo Original - owner edited | Documented personal account | Chinese classics | Ready candidate | Học hỏi & phát triển | Comparison | Tội lỗi | Đối thoại
Mixed emotions / Emotional memory |  | Hold |  |  |  | Parable |  | Literary episode | Japanese wisdom / Zen | Released | Nghỉ ngơi & sức khỏe tinh thần | Compassion | Xấu hổ | Trích đoạn triết học
Meaning / Identity / Work |  | Rejected |  |  |  | Historical case |  |  | Persian |  | Ý nghĩa & bản sắc | Control | Tức giận | Research-informed observation
AI-age Human Judgment | [5 empty] | Biography |  |  | Middle Eastern / Arabic |  | Thay đổi / mất mát / chuyển tiếp | Enoughness | Buồn | Story-derived insight
Relationships / Boundaries / Connection | [5 empty] | Research paper |  |  | African traditions |  | Xã hội & văn hóa | Failure | Cô đơn | Traditional wisdom
Rest / Limits / Wellbeing | [5 empty] | Institutional source |  |  | Jewish wisdom |  | AI & tương lai | Fear | Trống rỗng | Selflo Original
[6 empty] | Journalism |  |  | European folk |  |  | Grief | Tê liệt
[6 empty] | Secondary scholarship |  |  | World literature |  |  | Identity | Tiếc nuối
[6 empty] | Selflo Original |  |  | Modern philosophy |  |  | Impermanence | Nhẹ nhõm
[9 empty] | Psychology |  |  | Judgment | Hy vọng
[9 empty] | Human sciences |  |  | Meaning | Biết ơn
[9 empty] | Modern work |  |  | Patience | Áp lực
[9 empty] | AI-era research |  |  | Recovery | Quá tải
[9 empty] | Other |  |  | Responsibility | Bình yên
[12 empty] | Rest | Mixed / contradictory
[12 empty] | Self-worth | Lingering emotion
[12 empty] | Simplicity | Không gọi tên được
Trust
Uncertainty
Values
Connection
Learning
Hope
Mortality

## README
SELFLO — Wisdom, Quote & Story Research Library
Mục | Giải thích | V2 — CÁCH HIỂU TAXONOMY
Mục tiêu | Xây kho nguyên liệu lớn cho Selflo trước khi curate Release. Thu thập rộng, xác minh nguồn, chuẩn hóa, phân loại; KHÔNG mặc định nội dung thu thập sẽ được Release. | Life Area | Vùng đời sống rộng: Công việc, Quan hệ, Nội tâm...
Pipeline | Collect → Verify & Normalize → Classify → Selflo Fit Review → Release Curation → Story Selection/Adaptation. | Human Experience | Trải nghiệm cụ thể. Đây là đơn vị coverage chính.
Ưu tiên nguồn | Primary/authoritative source trước. Tránh Pinterest/quote-card/random quote aggregators nếu không truy được nguồn gốc. | Theme | Ý tưởng/khái niệm được content chạm tới.
Quote hiện đại | Đặc biệt kiểm tra fake attribution. Một câu hay nhưng nguồn yếu vẫn có thể giữ Research Pool với Verification C/D, không được tự động Release. | Emotion / State | Cảm xúc/trạng thái biên tập; không phải chẩn đoán.
Selflo Original | Chỉ tạo khi external source không phủ tốt. Phải ghi rõ Selflo Original / AI-assisted draft; không gán cho tác giả khác và không paraphrase để né copyright. | Editorial Role | Quote làm gì: nhận ra, gọi tên, cho phép, đổi góc nhìn, phân biệt, trả quyền lựa chọn.
Story | Chỉ lưu story/parables/historical/research/journalism có provenance rõ. Không tự bịa story để lấp coverage. | Content Form | Cách thể hiện: quan sát, ẩn dụ, câu hỏi, tục ngữ, thơ...
Principle Library | Lưu nguyên lý từ philosophy, psychology, human sciences và tài liệu AI. Principle là research seed; không mặc định là quote cho user. | Principle | Triết lý/research đứng phía sau.
Coverage | Theo dõi cả cluster và human experience. Mục tiêu 50 item/cluster là target research pool, không phải quota Release. | Coverage | Không phải chỉ đếm quote. Xem breadth + role diversity + source diversity + form diversity + quality.
Editorial roles | Recognize / Name / Permit / Reframe / Distinguish / Return agency. Một item có thể có Primary Role + Secondary Role.
Verification | A = primary source; B = authoritative secondary; C = plausible nhưng chưa có primary; D = disputed/internet-only; N/A = Selflo Original.
Rights | Tách quality khỏi rights. Nội dung copyrighted vẫn có thể lưu Research Pool nhưng phải đánh dấu research-only/permission needed.
Cách dùng với AI | Chọn một dòng trong 90-Day Plan, giao AI thực hiện theo AI Collection Guide, sau đó nhập kết quả vào Quote/Story/Principle/Source Library và cập nhật Actual.
Quy tắc không bịa | Nếu không tìm được source URL/work/chapter đáng tin: để trống hoặc đánh dấu Needs Verification. Không tự tạo URL, tác giả, tác phẩm, câu chuyện hay provenance.

## 90-Day Plan
Day | Phase | Collection Focus | Primary Sources / Traditions | What to Collect | Quote Target | Story Target | Principle Target | Quote Actual | Story Actual | Principle Actual | Status | Progress % | Notes
1 | A. Ancient Foundations | Laozi I | Tao Te Ching ch. 1–20 | Passages on opposites, desire, knowing, simplicity; original Chinese + chapter + working VI | 20 | 1 | 4 |  |  |  | Planned | 0%
2 | A. Ancient Foundations | Laozi II | Tao Te Ching ch. 21–50 | Non-action, softness, enoughness, humility, change | 20 | 1 | 4 |  |  |  | Planned | 0%
3 | A. Ancient Foundations | Laozi III | Tao Te Ching ch. 51–81 | Loss/gain, control, contentment, strength/softness; deduplicate Laozi | 20 | 1 | 4 |  |  |  | Planned | 0%
4 | A. Ancient Foundations | Zhuangzi | Zhuangzi primary text | Passages + parables: Butterfly Dream, Empty Boat, Useless Tree, Cook Ding, etc. | 20 | 7 | 5 |  |  |  | Planned | 0%
5 | A. Ancient Foundations | Liezi | Liezi | Passages + traceable stories | 20 | 4 | 4 |  |  |  | Planned | 0%
6 | A. Ancient Foundations | Huainanzi | Huainanzi | Passages + parables including Sai Weng; change/judgment/fortune | 20 | 5 | 4 |  |  |  | Planned | 0%
7 | A. Ancient Foundations | Epictetus | Enchiridion / Discourses | Control, judgment, desire, externals, agency | 22 | 2 | 4 |  |  |  | Planned | 0%
8 | A. Ancient Foundations | Marcus Aurelius | Meditations | Time, judgment, change, mortality, social life | 22 | 1 | 4 |  |  |  | Planned | 0%
9 | A. Ancient Foundations | Seneca | Letters / Essays | Time, adversity, wealth, anger, friendship, mortality | 22 | 2 | 4 |  |  |  | Planned | 0%
10 | A. Ancient Foundations | Musonius Rufus + Stoic fragments | Lectures / fragments | Practice, simplicity, character; disputed attribution review | 18 | 1 | 3 |  |  |  | Planned | 0%
11 | A. Ancient Foundations | Dhammapada | Dhammapada | Mind, attention, impermanence, conduct, suffering | 22 | 1 | 4 |  |  |  | Planned | 0%
12 | A. Ancient Foundations | Majjhima Nikaya | Selected suttas | Passages + metaphors/parables such as raft where sourced | 18 | 4 | 4 |  |  |  | Planned | 0%
13 | A. Ancient Foundations | Samyutta / Anguttara Nikaya | Selected suttas | Impermanence, attachment, perception, compassion, attention | 20 | 3 | 4 |  |  |  | Planned | 0%
14 | A. Ancient Foundations | Early Buddhist parables | Early canonical / reputable collections | Traceable parables and metaphors; provenance first | 16 | 7 | 4 |  |  |  | Planned | 0%
15 | A. Ancient Foundations | Socrates / Plato | Plato dialogues | Knowing/not knowing, virtue, examined life, friendship | 20 | 1 | 4 |  |  |  | Planned | 0%
16 | A. Ancient Foundations | Aristotle | Nicomachean Ethics + selected works | Flourishing, habit, friendship, virtue, choice | 20 | 1 | 4 |  |  |  | Planned | 0%
17 | A. Ancient Foundations | Epicurus | Letters / Principal Doctrines / fragments | Desire, enoughness, friendship, mortality | 20 | 1 | 4 |  |  |  | Planned | 0%
18 | A. Ancient Foundations | Bhagavad Gita | Bhagavad Gita | Action, attachment, duty, equanimity; retain original location | 20 | 1 | 4 |  |  |  | Planned | 0%
19 | A. Ancient Foundations | Upanishads | Selected Upanishads | Self, change, knowledge, mortality; careful translation provenance | 20 | 1 | 4 |  |  |  | Planned | 0%
20 | A. Ancient Foundations | Panchatantra | Panchatantra | Wisdom passages + traceable animal/human stories | 18 | 7 | 4 |  |  |  | Planned | 0%
21 | B. World Wisdom | Vietnamese ca dao | Authoritative Vietnamese collections | Ca dao on life, family, work, endurance, relationships | 25 | 2 | 2 |  |  |  | Planned | 0%
22 | B. World Wisdom | Vietnamese proverbs | Authoritative proverb dictionaries/collections | Proverbs; source collection and variant tracking | 25 | 2 | 3 |  |  |  | Planned | 0%
23 | B. World Wisdom | Nguyễn Trãi + Nguyễn Bỉnh Khiêm | Primary/critical editions | Passages on life, change, enoughness, public/private life | 20 | 1 | 3 |  |  |  | Planned | 0%
24 | B. World Wisdom | Nguyễn Du + classical Vietnamese literature | Primary/critical editions | Human experience, fate, compassion, contradiction, impermanence | 20 | 2 | 3 |  |  |  | Planned | 0%
25 | B. World Wisdom | Confucius | Analects | Learning, relationships, self-cultivation, judgment | 20 | 1 | 4 |  |  |  | Planned | 0%
26 | B. World Wisdom | Mencius | Mencius | Human nature, courage, values, social responsibility | 20 | 1 | 4 |  |  |  | Planned | 0%
27 | B. World Wisdom | Chinese idioms/proverbs | Authoritative dictionaries/classical sources | Traceable idioms/proverbs; avoid unsourced internet variants | 22 | 3 | 3 |  |  |  | Planned | 0%
28 | B. World Wisdom | Japanese proverbs | Authoritative Japanese collections | Traditional wisdom with Japanese original and provenance | 22 | 2 | 3 |  |  |  | Planned | 0%
29 | B. World Wisdom | Dōgen / Zen sources | Primary Zen texts / reputable translations | Practice, presence, impermanence; separate later anecdotes | 18 | 3 | 4 |  |  |  | Planned | 0%
30 | B. World Wisdom | Bashō + Ryōkan | Primary/critical editions | Short passages/poems usable as research; copyright/public-domain notes | 18 | 2 | 3 |  |  |  | Planned | 0%
31 | B. World Wisdom | Saadi | Gulistan / Bustan | Human conduct, humility, relationships, fortune | 20 | 4 | 3 |  |  |  | Planned | 0%
32 | B. World Wisdom | Rumi + Hafez | Primary texts / scholarly translations | Love, loss, longing, change; aggressive fake-quote checking | 18 | 2 | 3 |  |  |  | Planned | 0%
33 | B. World Wisdom | Arabic / Middle Eastern proverbs | Authoritative regional collections | Region-specific proverbs; avoid generic attribution | 22 | 3 | 3 |  |  |  | Planned | 0%
34 | B. World Wisdom | Middle Eastern wisdom stories | Primary/reputable collections | Parables, historical wisdom episodes, traceable folk material | 15 | 7 | 3 |  |  |  | Planned | 0%
35 | B. World Wisdom | African traditions I | Akan / Yoruba sources | Culture-specific proverbs + stories with provenance | 22 | 3 | 3 |  |  |  | Planned | 0%
36 | B. World Wisdom | African traditions II | Igbo / Swahili sources | Culture-specific proverbs + stories with provenance | 22 | 3 | 3 |  |  |  | Planned | 0%
37 | B. World Wisdom | African traditions III | Ethiopian / other well-sourced traditions | Fill cultural gaps; reject generic 'African proverb' when unsourced | 20 | 3 | 3 |  |  |  | Planned | 0%
38 | B. World Wisdom | Jewish wisdom traditions | Primary/reputable texts | Wisdom passages, stories, human dilemmas | 20 | 3 | 3 |  |  |  | Planned | 0%
39 | B. World Wisdom | European folk proverbs | English/French/German/Italian/Spanish collections | Traceable proverbs; variants and earliest source if feasible | 25 | 3 | 2 |  |  |  | Planned | 0%
40 | B. World Wisdom | Cross-cultural review | All Phase B sources | Deduplicate, provenance audit, cultural balance, gap report | 5 | 0 | 5 |  |  |  | Planned | 0%
41 | C. Literature & Modern Thought | Tolstoy | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
42 | C. Literature & Modern Thought | Dostoevsky | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
43 | C. Literature & Modern Thought | Chekhov | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
44 | C. Literature & Modern Thought | Hermann Hesse | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
45 | C. Literature & Modern Thought | Kafka | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
46 | C. Literature & Modern Thought | Camus | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
47 | C. Literature & Modern Thought | Virginia Woolf | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
48 | C. Literature & Modern Thought | Rilke | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
49 | C. Literature & Modern Thought | Montaigne | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
50 | C. Literature & Modern Thought | Kierkegaard | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
51 | C. Literature & Modern Thought | Simone Weil | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
52 | C. Literature & Modern Thought | Hannah Arendt | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
53 | C. Literature & Modern Thought | Tagore | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
54 | C. Literature & Modern Thought | Modern Asian literature / thought | Primary/critical editions; reputable archives | Passages on lived human experience; record work/chapter/page; flag copyright | 20 | 2 | 3 |  |  |  | Planned | 0%
55 | C. Literature & Modern Thought | Literature coverage review | Phase C corpus | Deduplicate; map loneliness, uncertainty, identity, grief, meaning, ordinary life, contradiction, work, love, choice | 5 | 0 | 5 |  |  |  | Planned | 0%
56 | D. Psychology & Human Science | William James | Primary works / archives | Attention, habit, experience, choice; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
57 | D. Psychology & Human Science | Carl Rogers | Primary works / reputable archives | Acceptance, congruence, listening, self; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
58 | D. Psychology & Human Science | Viktor Frankl | Primary works / Frankl Institute | Meaning, freedom, responsibility; fake attribution audit; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
59 | D. Psychology & Human Science | Self-compassion research | Peer-reviewed research / institutional sources | Self-kindness, common humanity, self-criticism; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
60 | D. Psychology & Human Science | Psychological flexibility / ACT | Peer-reviewed research | Values, acceptance, flexibility, action; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
61 | D. Psychology & Human Science | Affect labeling | Peer-reviewed research | Naming emotions; effects and limitations; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
62 | D. Psychology & Human Science | Mixed emotions | Peer-reviewed research | Co-occurring positive/negative emotions; bittersweet states; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
63 | D. Psychology & Human Science | Rumination | Peer-reviewed research | Repetitive thought, mood, attention; limitations; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
64 | D. Psychology & Human Science | Psychological detachment from work | Peer-reviewed research | Work carryover, recovery, switching off; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
65 | D. Psychology & Human Science | Recovery / fatigue / burnout | Peer-reviewed research / WHO where relevant | Recovery, workload, fatigue; avoid diagnosis creep; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
66 | D. Psychology & Human Science | Uncertainty tolerance | Peer-reviewed research | Ambiguity, intolerance of uncertainty, waiting; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
67 | D. Psychology & Human Science | Decision making | Decision science research | Trade-offs, judgment, irreversible/reversible decisions; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
68 | D. Psychology & Human Science | Choice / choice overload | Peer-reviewed research | Choice set, moderators, judgment bottlenecks; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
69 | D. Psychology & Human Science | Comparison / self-evaluation | Peer-reviewed research | Social comparison, standards, self-worth; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
70 | D. Psychology & Human Science | Meaning / identity / values | Peer-reviewed research | Meaning-making, identity, values, work identity; extract finding + limitation + Selflo principle seed | 8 | 1 | 8 |  |  |  | Planned | 0%
71 | E. Modern Life & AI Age | Abundance → scarcity migration | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
72 | E. Modern Life & AI Age | Attention scarcity | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
73 | E. Modern Life & AI Age | Information abundance / noise | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
74 | E. Modern Life & AI Age | Choice → judgment bottleneck | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
75 | E. Modern Life & AI Age | Trust / verification | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
76 | E. Modern Life & AI Age | Fast execution / slow cognition | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
77 | E. Modern Life & AI Age | Learning-by-doing | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
78 | E. Modern Life & AI Age | Skill atrophy / cognitive offloading | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
79 | E. Modern Life & AI Age | Competition → baseline | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
80 | E. Modern Life & AI Age | Productivity ≠ leisure | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
81 | E. Modern Life & AI Age | Path dependence | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
82 | E. Modern Life & AI Age | Human agency in AI-rich environments | AI-era docs + economics/history/psychology/human factors sources | Find historical analogies, research findings, external wisdom; create Selflo Original seeds only after source-backed research | 12 | 2 | 8 |  |  |  | Planned | 0%
83 | F. Coverage Gap Filling | Exhaustion / Recovery / Rest | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
84 | F. Coverage Gap Filling | Self-compassion / Self-blame | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
85 | F. Coverage Gap Filling | Uncertainty / Choice / Agency | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
86 | F. Coverage Gap Filling | Comparison / External standards / Values | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
87 | F. Coverage Gap Filling | Attention / Silence / Presence | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
88 | F. Coverage Gap Filling | Learning / Failure / Quiet growth | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
89 | F. Coverage Gap Filling | Identity / Meaning / Work / Change | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%
90 | F. Coverage Gap Filling | Mixed emotions / Emotional memory + final audit | Whole collected library + targeted authoritative sources | Fill under-covered human experiences only; prefer sources/traditions not yet overrepresented; final day produces coverage audit | 20 | 3 | 4 |  |  |  | Planned | 0%

## Quote Library
Quote ID | Status | Cluster Primary | Cluster Secondary | Human Experience | Editorial Role Primary | Editorial Role Secondary | Quote Text - Original | Language | Quote Text - Working VI | Author / Attribution | Tradition / Region | Source Title | Work / Chapter / Location | Source URL | Source Type | Quote Type | Verification Grade | Verification Notes | Rights Status | Copyright / Usage Notes | Selflo Fit | Selflo Fit Notes | Directive Risk | Overlap / Duplicate Risk | Related Principle ID(s) | Related Story ID(s) | Story Dependency Gate | Owner Review | Release Readiness | Current Library Location | Collected Day | Collected By | Date Collected | Notes

## Story Library
Story ID | Status | Title | Original / Local Title | Story Type | Tradition / Region | Cluster Primary | Cluster Secondary | Human Experience | Summary (research only) | Primary Source / Work | Source Location | Source URL | Secondary Verification URL | Verification Grade | Verification Notes | Rights Status | Copyright / Adaptation Notes | Historical / Traditional Context | Key Principle ID(s) | Related Quote ID(s) | Selflo Fit | Selflo Fit Notes | Adaptation Allowed? | Human Edited? | Rights Verified? | Story Gate Status | Current Library Location | Collected Day | Collected By | Date Collected | Notes

## Principle Library
Principle ID | Status | Principle Name | Domain | Definition / Claim | Source Title | Source Author / Institution | Source URL | Source Type | Evidence / Basis | Limitations / Counterpoints | Verification Grade | Related AI-doc Principle | Human Experience Link | Cluster Primary | Editorial Relevance | Related Quote ID(s) | Related Story ID(s) | Selflo Use | Selflo Original Seed Allowed? | Collected Day | Notes

## Source Registry
Source ID | Author / Tradition | Culture / Region | Source Title | Source Type | Original Language | Approx. Date / Era | Primary URL | Secondary Verification URL | Reliability Tier | Public Domain? | Rights Notes | Used for Quote IDs | Used for Story IDs | Used for Principle IDs | First Collected Day | Verification Notes

## Coverage Map
SELFLO COVERAGE MAP — Research Pool
Cluster | Target Pool | Quote Count | Story Count | Principle Count | Verified A/B Quotes | High Selflo Fit | Released Quotes | Gap | Coverage % | Priority | Notes
Exhaustion / Recovery / Work carryover | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Self-compassion / Self-blame | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Uncertainty / Choice / Agency | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Comparison / External standards / Values | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Attention / Noise / Deep focus | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Learning / Failure / Quiet growth | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Change / Impermanence / Recovery | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Mixed emotions / Emotional memory | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Meaning / Identity / Work | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
AI-age Human Judgment | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Relationships / Boundaries / Connection | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High
Rest / Limits / Wellbeing | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0% | High

## Dashboard
SELFLO WISDOM LIBRARY — DASHBOARD
Metric | Value
Quotes collected | 0
Quotes verified A/B | 0
Quotes high Selflo fit | 0
Released quotes | 0
Stories collected | 0
Stories gate passed | 0
Principles collected | 0
Sources registered | 0
90-day tasks done | 0
90-day progress | 0%
Cluster | Quote Count | Target | Coverage %
Exhaustion / Recovery / Work carryover | 0 | 50 | 0%
Self-compassion / Self-blame | 0 | 50 | 0%
Uncertainty / Choice / Agency | 0 | 50 | 0%
Comparison / External standards / Values | 0 | 50 | 0%
Attention / Noise / Deep focus | 0 | 50 | 0%
Learning / Failure / Quiet growth | 0 | 50 | 0%
Change / Impermanence / Recovery | 0 | 50 | 0%
Mixed emotions / Emotional memory | 0 | 50 | 0%
Meaning / Identity / Work | 0 | 50 | 0%
AI-age Human Judgment | 0 | 50 | 0%
Relationships / Boundaries / Connection | 0 | 50 | 0%
Rest / Limits / Wellbeing | 0 | 50 | 0%

## AI Collection Guide
AI COLLECTION GUIDE — dùng workbook này để giao việc từng ngày
Step | Instruction | Required Output | Do Not | Quality Gate | Where to Save
1 | Chọn Day trong 90-Day Plan. Dùng đúng Collection Focus, Sources/Traditions và What to Collect của ngày đó. | Danh sách candidate + source evidence. | Không tự đổi sang chủ đề khác chỉ vì dễ tìm. | Ưu tiên primary/authoritative sources. | 90-Day Plan
2 | Thu quote/passages rộng; chưa lọc quá sớm theo Selflo fit. | Original text, working VI, author/tradition, work/chapter, URL, quote type. | Không dùng quote aggregator làm nguồn cuối nếu có thể truy primary. | Wording và attribution phải traceable. | Quote Library
3 | Với proverb/folk wisdom, xác định culture/region/collection càng cụ thể càng tốt. | Variant, tradition, source collection, URL. | Không ghi generic 'African proverb' nếu không xác định được. | Nếu provenance yếu → Verification C/D. | Quote Library + Source Registry
4 | Thu story/parables/cases chỉ khi có provenance. | Title, summary, source work/location, URL, story type, context. | Không tự bịa hoặc ghép nhiều chuyện thành một chuyện thật. | Story không nguồn → không nhập như verified story. | Story Library
5 | Với psychology/research, lưu finding chứ không biến finding thành quote của researcher. | Finding, source paper, limitation, principle seed. | Không tạo fake quote từ abstract/conclusion. | Phải có limitation/counterpoint nếu source hỗ trợ. | Principle Library
6 | Nếu external sources không phủ một human experience, có thể tạo Selflo Original seed. | Label Selflo Original - AI-assisted draft + research basis. | Không gán cho tác giả khác; không paraphrase tác phẩm copyrighted để né quyền. | Chỉ là seed, chưa Release. | Quote Library
7 | Đăng ký source/tác giả/tradition mới. | Source ID, title, author, language, URL, reliability tier, rights notes. | Không tạo URL hoặc bibliographic detail không kiểm chứng. | Tier 1/2 ưu tiên. | Source Registry
8 | Cập nhật Actual + Status sau khi nhập library. | Quote/Story/Principle Actual, notes, status Done/In progress. | Không đánh Done nếu dữ liệu chưa được nhập. | Actual phải khớp số item thực nhập. | 90-Day Plan
Prompt mẫu giao cho AI
Thực hiện [DAY X] trong workbook Selflo Wisdom Library. 1) Bám đúng Collection Focus / Primary Sources / What to Collect. 2) Internet-first, ưu tiên primary hoặc authoritative sources. 3) Thu thập rộng cho Research Pool; chưa loại chỉ vì chưa hoàn toàn Selflo-fit. 4) Mỗi quote phải có original wording nếu có, author/tradition, source title, work/chapter/location, source URL, quote type và verification grade. 5) Phân biệt verbatim / published translation / working translation / paraphrase / proverb / Selflo Original. 6) Không bịa nguồn, URL, tác giả, story hoặc provenance. Attribution không chắc phải đánh C/D. 7) Story chỉ thu nếu có nguồn rõ. Research finding không được biến thành quote. 8) Gắn cluster, human experience và editorial role sơ bộ. 9) Báo các quote bị loại vì fake attribution hoặc không truy được nguồn. 10) Trả output theo đúng cột của Quote Library, Story Library, Principle Library và Source Registry; cuối cùng báo Actual để cập nhật 90-Day Plan.

## Daily Log
Date | Day | Phase | Focus | Quotes Added | Stories Added | Principles Added | Sources Added | Verification A/B | Rejected / Disputed | Key Discoveries | Coverage Gaps Found | Next Action

## Human Experience Map
Experience ID | Cluster | Human Experience / Tension | User-like Example | Needed Editorial Job | Quote Target | Quote Actual | Story Actual | Principle Actual | Coverage Status | Notes
EXP-001 | Exhaustion / Recovery / Work carryover | Nhiều việc nhỏ làm cạn năng lượng | Không có việc nào quá lớn, sao mình vẫn mệt? | Name / Permit | 8 | 0 | 0 | 0 | Gap
EXP-002 | Exhaustion / Recovery / Work carryover | Công việc còn ở lại sau giờ làm | Mình về nhà rồi nhưng đầu vẫn ở công ty. | Recognize / Name | 8 | 0 | 0 | 0 | Gap
EXP-003 | Exhaustion / Recovery / Work carryover | Sự kiện đã qua nhưng hồi phục chưa xong | Chuyện qua rồi, sao mình vẫn chưa ổn? | Recognize / Permit / Distinguish | 8 | 0 | 0 | 0 | Gap
EXP-004 | Self-compassion / Self-blame | Đã gây hậu quả và đang tự trách | Mình làm sai nên rất khó chịu với chính mình. | Distinguish / Permit | 8 | 0 | 0 | 0 | Gap
EXP-005 | Self-compassion / Self-blame | Đang học nhưng thấy mình kém | Mình còn vụng; có phải mình không đủ tốt? | Reframe / Permit | 8 | 0 | 0 | 0 | Gap
EXP-006 | Uncertainty / Choice / Agency | Chưa biết và chưa cần quyết định ngay | Mình vẫn chưa biết mình muốn gì. | Permit / Return agency | 8 | 0 | 0 | 0 | Gap
EXP-007 | Uncertainty / Choice / Agency | Quá nhiều câu trả lời | Càng hỏi thêm mình càng khó chọn. | Distinguish / Return agency | 8 | 0 | 0 | 0 | Gap
EXP-008 | Uncertainty / Choice / Agency | Hai lựa chọn đều có điều đáng giữ | Ở lại có cái mất; đi cũng có cái mất. | Recognize / Permit | 8 | 0 | 0 | 0 | Gap
EXP-009 | Comparison / External standards / Values | Thành công của người khác làm mình thấy nhỏ đi | Người khác tiến lên còn mình đứng yên. | Reframe | 8 | 0 | 0 | 0 | Gap
EXP-010 | Comparison / External standards / Values | Sống bằng thước đo bên ngoài | Mình đang dùng tiêu chuẩn của ai để đánh giá đời mình? | Distinguish / Return agency | 8 | 0 | 0 | 0 | Gap
EXP-011 | Attention / Noise / Deep focus | Tiếp nhận nhiều nhưng không nghe được mình | Cả ngày có quá nhiều tiếng nói. | Recognize / Distinguish | 8 | 0 | 0 | 0 | Gap
EXP-012 | Learning / Failure / Quiet growth | Tiến bộ âm thầm | Mình không thấy mình tiến bộ gì. | Recognize / Reframe | 8 | 0 | 0 | 0 | Gap
EXP-013 | Mixed emotions / Emotional memory | Hai cảm xúc trái chiều cùng tồn tại | Mình vừa nhẹ nhõm vừa buồn. | Permit / Distinguish | 8 | 0 | 0 | 0 | Gap
EXP-014 | Mixed emotions / Emotional memory | Trải nghiệm cũ đi vào phản ứng mới | Sao chuyện nhỏ này lại làm mình phản ứng mạnh vậy? | Recognize / Name | 8 | 0 | 0 | 0 | Gap
EXP-015 | Meaning / Identity / Work | Bản sắc khi công việc thay đổi | Nếu công việc này không còn, mình còn là ai? | Recognize / Return agency | 8 | 0 | 0 | 0 | Gap
EXP-016 | AI-age Human Judgment | Nhiều output nhưng judgment vẫn là của mình | Có rất nhiều câu trả lời, nhưng câu nào thật sự là của mình? | Distinguish / Return agency | 8 | 0 | 0 | 0 | Gap

## Taxonomy VN
SELFLO TAXONOMY — HƯỚNG DẪN PHÂN LOẠI & COVERAGE
Tầng | Tên taxonomy | Câu hỏi taxonomy trả lời | Ví dụ | Dùng để đánh giá coverage | Ghi chú
1 | Lĩnh vực cuộc sống (Life Area) | Người dùng đang ở vùng nào của đời sống? | Công việc; Nội tâm; Quan hệ; Gia đình; Nghỉ ngơi | Độ rộng các vùng đời sống | Không dùng Life Area thay cho trải nghiệm cụ thể.
2 | Trải nghiệm con người (Human Experience) | Điều gì cụ thể đang xảy ra với người dùng? | Công việc vẫn ở trong đầu sau giờ làm | Đây là đơn vị coverage QUAN TRỌNG NHẤT | Một Life Area có nhiều Human Experience.
3 | Chủ đề (Theme) | Những ý tưởng nào đang được chạm tới? | Recovery; Attention; Boundaries | Độ rộng ý niệm | Một Experience có thể có nhiều Theme.
4 | Cảm xúc / trạng thái (Emotion / State) | Người dùng có thể đang cảm thấy/trải qua trạng thái gì? | Mệt; lo; bối rối; tiếc nuối; nhẹ nhõm | Coverage theo trạng thái cảm xúc | Không chẩn đoán người dùng; đây là tag biên tập.
5 | Vai trò biên tập (Editorial Role) | Nội dung đang làm gì cho người đọc? | Recognize; Name; Permit; Reframe; Distinguish; Return agency | Độ đa dạng góc nhìn trong cùng Experience | Tránh library chỉ toàn Reframe/inspiration.
6 | Hình thức nội dung (Content Form) | Câu được thể hiện bằng cách nào? | Quan sát; ẩn dụ; câu hỏi; nghịch lý; tục ngữ; thơ | Độ đa dạng giọng và hình thức | Tránh 1.000 câu nhưng đều cùng kiểu viết.
7 | Nguyên lý nền (Principle) | Research/triết lý nào đứng phía sau? | Psychological detachment; mixed emotions; human agency | Độ sâu tri thức | Principle thường không cần hiện trực tiếp với user.
8 | Nguồn / truyền thống (Source / Tradition) | Nội dung đến từ đâu? | Đạo gia; Stoicism; Việt Nam; Literature; Psychology | Độ đa dạng văn hóa/tác giả/nguồn | Theo dõi over-representation.
9 | Mức xác minh (Verification) | Attribution/source đáng tin tới đâu? | A primary; B authoritative; C needs primary; D disputed | Chất lượng provenance | D vẫn có thể giữ research nhưng không tự động Release.
10 | Quyền sử dụng (Rights) | Có thể dùng nội dung như thế nào? | Public domain; copyrighted; permission needed | Khả năng sử dụng thực tế | Tách quality khỏi rights.
11 | Mức phù hợp Selflo (Selflo Fit) | Nội dung có hợp triết lý Selflo không? | High / Medium / Low / Not reviewed | Chỉ dùng ở phase curate | Không lọc quá sớm trong giai đoạn Collect.
COVERAGE NGHĨA LÀ GÌ?
Mức | Ý nghĩa | Quy tắc gợi ý | Ví dụ | Hành động
🔴 Missing | Chưa có nội dung cho trải nghiệm. | 0 quote phù hợp. | Mixed emotions: 0 | Ưu tiên collect.
🟠 Thin | Có nội dung nhưng góc nhìn còn mỏng. | 1–2 quote hoặc chỉ 1 editorial role. | Chỉ có Reframe. | Tìm thêm nguồn/góc nhìn khác.
🟡 Covered | Đã có nhiều góc nhìn đủ dùng. | ≥3 quote và ≥2 editorial roles, nguồn không quá lệch. | Recognize + Permit + Distinguish. | Không cần ép thêm số lượng.
🟢 Rich | Coverage giàu và đa dạng. | Nhiều editorial roles + source/form diversity + story/principle khi hữu ích. | Quote + story + research + nhiều truyền thống. | Chỉ bổ sung khi có giá trị mới.
VÍ DỤ PHÂN LOẠI MỘT QUOTE
Quote | Mưa đã tạnh. Mặt đất chưa khô. Nhưng mưa đã tạnh.
Life Area | Nội tâm & cảm xúc
Human Experience | Chuyện đã qua nhưng mình chưa hồi phục
Theme | Recovery; Impermanence
Emotion / State | Lingering emotion; mệt; buồn (tag biên tập, không chẩn đoán)
Editorial Role | Recognize + Permit
Content Form | Ẩn dụ (Metaphor)
Source | Selflo Original
Selflo Fit | High

## Quote Library v2
Quote ID | Trạng thái | Lĩnh vực cuộc sống (Life Area) | Cluster chính | Cluster phụ | Trải nghiệm con người (Human Experience) | Chủ đề chính (Theme) | Chủ đề phụ | Cảm xúc / trạng thái chính | Cảm xúc / trạng thái phụ | Vai trò biên tập chính | Vai trò biên tập phụ | Hình thức nội dung (Content Form) | Nguyên văn | Ngôn ngữ | Bản dịch / bản làm việc tiếng Việt | Tác giả / Attribution | Truyền thống / khu vực | Tên nguồn / tác phẩm | Chương / vị trí | Source URL | Loại nguồn | Loại quote | Mức xác minh | Ghi chú xác minh | Quyền sử dụng | Ghi chú copyright / usage | Mức phù hợp Selflo | Ghi chú Selflo Fit | Rủi ro giáo điều / directive | Rủi ro trùng ý | Principle ID liên quan | Story ID liên quan | Story dependency gate | Owner review | Release readiness | Vị trí library hiện tại | Ngày trong plan | Người thu thập | Ngày thu thập | Ghi chú

## Coverage Matrix
COVERAGE MATRIX — HUMAN EXPERIENCE × EDITORIAL ROLE
Trải nghiệm con người | Recognize | Name | Permit | Reframe | Distinguish | Return agency | Coverage Level
Những việc nhỏ tích lũy làm cạn năng lượng | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Công việc còn ở lại trong đầu sau giờ làm | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Chuyện đã qua nhưng mình chưa hồi phục | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Đã gây hậu quả và đang tự trách | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Đang học nhưng cảm thấy mình kém | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Capacity thấp bị hiểu thành giá trị bản thân thấp | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Thành công của người khác làm mình thấy nhỏ đi | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Đang sống bằng thước đo bên ngoài | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Chưa biết mình muốn gì | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Có quá nhiều câu trả lời / lựa chọn | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Hai lựa chọn đều có điều đáng giữ và cái mất | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Đã chọn nhưng vẫn tiếc lựa chọn còn lại | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Tiếp nhận quá nhiều nên khó nghe được mình | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Tiến bộ diễn ra âm thầm | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Thất bại khi đang học | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Vừa nhẹ nhõm vừa buồn | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Vừa muốn ở lại vừa muốn rời đi | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Yêu thương và tức giận cùng tồn tại | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Trải nghiệm cũ đi vào phản ứng hiện tại | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Bản sắc thay đổi khi công việc thay đổi | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Không còn thấy ý nghĩa trong điều từng quan trọng | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Muốn nghỉ nhưng cảm thấy có lỗi | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Giới hạn năng lượng / cần nghỉ | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Không gọi tên được điều đang xảy ra bên trong | 0 | 0 | 0 | 0 | 0 | 0 | Missing
Nhiều output/AI answer nhưng judgment vẫn thuộc về mình | 0 | 0 | 0 | 0 | 0 | 0 | Missing

## Diversity Dashboard
DIVERSITY DASHBOARD — NGUỒN, HÌNH THỨC, LIFE AREA
Lĩnh vực cuộc sống | Số quote | Tỷ trọng | Editorial Role | Số quote | Tỷ trọng
Nội tâm & hiểu mình | 0 | 0% | Recognize | 0 | 0%
Cảm xúc | 0 | 0% | Name | 0 | 0%
Công việc & mục đích | 0 | 0% | Permit | 0 | 0%
Quan hệ | 0 | 0% | Reframe | 0 | 0%
Gia đình | 0 | 0% | Distinguish | 0 | 0%
Lựa chọn & định hướng | 0 | 0% | Return agency | 0 | 0%
Học hỏi & phát triển | 0 | 0%
Nghỉ ngơi & sức khỏe tinh thần | 0 | 0%
Ý nghĩa & bản sắc | 0 | 0% | Nguồn / truyền thống | Số quote | Tỷ trọng
Thay đổi / mất mát / chuyển tiếp | 0 | 0% | Taoism | 0 | 0%
Xã hội & văn hóa | 0 | 0% | Stoicism | 0 | 0%
AI & tương lai | 0 | 0% | Early Buddhism | 0 | 0%
|  |  | Vietnamese wisdom | 0 | 0%
|  |  | Chinese classics | 0 | 0%
Hình thức nội dung | Số quote | Tỷ trọng | Japanese wisdom / Zen | 0 | 0%
Quan sát trực tiếp | 0 | 0% | Persian | 0 | 0%
Ẩn dụ | 0 | 0% | African traditions | 0 | 0%
Câu hỏi | 0 | 0% | World literature | 0 | 0%
Nghịch lý | 0 | 0% | Modern philosophy | 0 | 0%
Tục ngữ / ca dao / thành ngữ | 0 | 0% | Psychology | 0 | 0%
Thơ / văn vần | 0 | 0% | AI-era research | 0 | 0%
Đối thoại | 0 | 0% | Other | 0 | 0%
Trích đoạn triết học | 0 | 0%
Research-informed observation | 0 | 0%
Story-derived insight | 0 | 0%
Traditional wisdom | 0 | 0%
Selflo Original | 0 | 0%